Unitarian Church of Montpelier
130 Main Street, Montpelier, Vermont 05602

Memorandum
To	Committee of Chairs
Fr	Peter Thoms, for the Stewardship Committee
Re	2018 Pledge Drive
Date	January 9, 2018

The Stewardship Committee proposes a 17-day pledge drive to take place in March. Below are a timeline for the drive, highlights for this year, and ways in which the Board and Committee of Chairs can be involved.
Timeline
Before the Drive
- Finance Committee, ET, and Board develop preliminary budget
- Based on preliminary budget, Stewardship determines pledge drive goal
  - Church Leadership, including Board and CoC, will be canvassed by the Stewardship Committee and Joan
Pledge Drive
- Day 1 - Saturday, March 10: Kickoff event, the Generosity Gathering, at Church
  • Intention: to receive 50% of pledge goal
  • Fine food and music
  • Joan speaks and others give testimonials
  • All members and friends are invited by weekly email announcements and pulpit announcement
- Day 2 - Sunday, March 11: Kickoff Sunday
- Joan gives sermon
- Additional testimonial(s)
  • Thank those who have pledged and give percentage of goal reached
  • Pledge email sent to all; pledging online will be available
- Day 3 - Monday, March 12: Pledge mailing sent to all remaining pledgers
- Day 9 - Sunday, March 18: Update from Stewardship Committee and additional testimonial(s). Updated email sent to all
• Day 16 - Sunday, March 25: “Commitment Sunday”
- Thanks to all who have given
- Possible testimonial(s)
- Commitment ritual
• Day 17 - Monday, March 26: Phone calls to all who have not yet pledged
Highlights of the Drive
- Commitment to recognize donors, as recommended by the UUA
- In light of comments and concerns about how public recognition of pledges was done last year, the Board has asked a group (Scott Hess, Ryan Kane, Nancy Read, Deb Robinson, and Peter Thoms) to review the questions and issues and to make recommendations to the Board, for adoption at its February 6th meeting
- Board members, at the January 2d meeting, affirmed public recognition of pledges in the Annual Report (unless anonymity is requested); the above group seeks to ensure that recognition criteria are simple, clear, and fair, and that they are communicated effectively
- Recognizing that volunteering for UCM is also significant stewardship in a wide range of ways, and is essential for the vitality and growth of the congregation, the group is also drafting a simple and clear way, on the form, for anyone to commit to giving volunteer hours to benefit UCM in the coming year
- “Generosity Gathering” dinner/event to kick-off pledge drive
- Focus on strategic priorities and congregational values vs. day-to-day expenses
- “Commitment” ritual
  - Enhanced involvement by Joan
    Board and CoC Involvement
- Lead by with generosity. It is hoped that Board and CoC members will be Leadership Donors
- Pledge early - prior to the pledge drive
- Help plan, put on, and attend the Generosity Gathering
- Help with Leadership Donor invitations to Generosity Gathering
- Give testimonials - individually or as a group
- Help with pledge drive mailing
- Make follow-up phone calls to those who have not pledged